## gantt chart data
Task | Start Date | End date | # Working Days | Task #
1.1 Initiating | 2020-05-18 | 2020-06-06 | 26 | 1.1
1.1.1 Project charter (PR1) | 2020-05-18 | 2020-05-25 | 16 | 1.1.1
1.1.2 Kick-off meeting (PR1) | 2020-05-26 | 2020-05-28 | 3 | 1.1.2
1.1.3 Team MBTI summary (PR1) | 2020-05-31 | 2020-06-02 | 3 | 1.1.3
1.1.4 Sponsor feedback (PR1) | 2020-06-03 | 2020-06-04 | 2 | 1.1.4
1.1.5 Google site initial set-up (PR1) | 2020-06-05 | 2020-06-06 | 2 | 1.1.5
1.2 Planning | 2020-06-08 | 2020-06-24 | 16 | 1.2
1.2.1 Draft scope statement (PR1) | 2020-06-08 | 2020-06-10 | 3 | 1.2.1
1.2.2 Team contract (PR1) | 2020-06-12 | 2020-06-14 | 3 | 1.2.2
1.2.3 Excel draft schedule (PR1) | 2020-06-15 | 2020-06-17 | 3 | 1.2.3
1.2.4 Gantt chart (PR2) | 2020-06-18 | 2020-06-20 | 3 | 1.2.4
1.2.6 Updated scope statement (PR2) | 2020-06-21 | 2020-06-22 | 2 | 1.2.5
1.2.5 Additional sponsor feedback (PR2) | 2020-06-23 | 2020-06-24 | 2 | 1.2.6
1.3 Executing | 2020-06-25 | 2020-07-30 | 31 | 1.3
1.3.1 Communications | 2020-06-25 | 2020-06-30 | 6 | 1.3.1
1.3.1.1 Document team meetings | 2020-06-25 | 2020-06-26 | 2 | 1.3.1.1
1.3.1.2 Document sponsor meetings/feedback | 2020-06-27 | 2020-06-28 | 2 | 1.3.1.2
1.3.1.3 Update Google site | 2020-06-29 | 2020-06-30 | 2 | 1.3.1.3
1.3.2 Nutrition Speacialist Module | 2020-07-01 | 2020-07-13 | 11 | 1.3.2
1.3.2.1 Login Screen of Nutrition Speacilist | 2020-07-01 | 2020-07-03 | 3 | 1.3.2.1
1.3.2.2 Verification of Nutrition Speacilist | 2020-07-05 | 2020-07-06 | 2 | 1.3.2.2
1.3.2.3 Uploading Nutrition Speacilist | 2020-07-08 | 2020-07-10 | 3 | 1.3.2.3
1.3.2.4 View Booking Information of Nutrition Speacilist | 2020-07-11 | 2020-07-13 | 3 | 1.3.2.4
1.3.3 Fitness Module | 2020-07-16 | 2020-07-30 | 14 | 1.3.3
1.3.3.1 Login Screen of Fitness Advisors | 2020-07-16 | 2020-07-17 | 2 | 1.3.3.1
1.3.3.2 View List of Fitness Advisors | 2020-07-18 | 2020-07-19 | 2 | 1.3.3.2
1.3.3.3 Select a Fitness Advisor | 2020-07-20 | 2020-07-22 | 2 | 1.3.3.3
1.3.3.4 Book Appointment | 2020-07-23 | 2020-07-25 | 3 | 1.3.3.4
1.3.3.5 Payment Gateway | 2020-07-26 | 2020-07-27 | 2 | 1.3.3.5
1.3.3.6 Confirmation Of Appointment | 2020-07-28 | 2020-07-30 | 3 | 1.3.3.6
1.4 Monitoring and Controlling | 2020-08-01 | 2020-09-10 | 35 | 1.4
1.4.1 Progress report 1 (PR1) | 2020-08-01 | 2020-08-10 | 10 | 1.4.1
1.4.1.1 Fill out progress report template | 2020-08-01 | 2020-08-03 | 3 | 1.4.1.1
1.4.1.2 Assemble all documents for PR1 | 2020-08-04 | 2020-08-05 | 2 | 1.4.1.2
1.4.1.3 Prepare and practice presentation | 2020-08-06 | 2020-08-07 | 2 | 1.4.1.3
1.4.1.5 Post all info online | 2020-08-08 | 2020-08-10 | 3 | 1.4.1.5
1.4.2 Progress report 2 (PR2) | 2020-08-12 | 2020-09-10 | 25 | 1.4.2
1.4.2.1 Fill out progress report template | 2020-08-12 | 2020-08-15 | 4 | 1.4.2.1
1.4.2.2 Prepare est. vs. actual hours summary | 2020-08-18 | 2020-08-21 | 4 | 1.4.2.2
1.4.2.3 Assemble all documents for PR2 | 2020-08-23 | 2020-08-27 | 5 | 1.4.2.3
1.4.2.4 Prepare and practice presentation | 2020-08-28 | 2020-08-30 | 3 | 1.4.2.4
1.2.2.5 Post all info online | 2020-09-01 | 2020-09-04 | 4 | 1.2.2.5
1.4.3 Other monitoring and controlling | 2020-09-05 | 2020-09-10 | 5 | 1.4.3
1.5 Closing | 2020-09-12 | 2020-10-04 | 16 | 1.5
1.5.1 Project notebook | 2020-09-12 | 2020-10-04 | 16 | 1.5.1
1.5.1.1 Assemble all documents for notebook | 2020-09-12 | 2020-09-15 | 4 | 1.5.1.1
1.5.1.2 Receive project completion form from sponsor | 2020-09-18 | 2020-09-20 | 3 | 1.5.1.2
1.5.1.3 Prepare final report | 2020-09-23 | 2020-09-26 | 4 | 1.5.1.3
1.5.1.4 Prepare and practice final presentation | 2020-09-29 | 2020-09-30 | 2 | 1.5.1.4
1.5.1.5 Post all info online | 2020-10-02 | 2020-10-03 | 2 | 1.5.1.5
1.5.1.6 Final presentation completed (milestone) | 2020-10-04 | 2020-10-04 | 1 | 1.5.1.6

## gantt chart
1.1 Initiating
1.1.1 Project charter (PR1)
1.1.2 Kick-off meeting (PR1)
1.1.3 Team MBTI summary (PR1)
1.1.4 Sponsor feedback (PR1)
1.1.5 Google site initial set-up (PR1)
1.2 Planning
1.2.1 Draft scope statement (PR1)
1.2.2 Team contract (PR1)
1.2.3 Excel draft schedule (PR1)
1.2.4 Gantt chart (PR2)
1.2.6 Updated scope statement (PR2)
1.2.5 Additional sponsor feedback (PR2)
1.3 Executing
1.3.1 Communications
1.3.1.1 Document team meetings
1.3.1.2 Document sponsor meetings/feedback
1.3.1.3 Update Google site
1.3.2 Nutrition Speacialist Module
1.3.2.1 Login Screen of Nutrition Speacilist
1.3.2.2 Verification of Nutrition Speacilist
1.3.2.3 Uploading Nutrition Speacilist
1.3.2.4 View Booking Information of Nutrition Speacilist
1.3.3 Fitness Module
1.3.3.1 Login Screen of Fitness Advisors
1.3.3.2 View List of Fitness Advisors
1.3.3.3 Select a Fitness Advisor
1.3.3.4 Book Appointment
1.3.3.5 Payment Gateway
1.3.3.6 Confirmation Of Appointment
1.4 Monitoring and Controlling
1.4.1 Progress report 1 (PR1)
1.4.1.1 Fill out progress report template
1.4.1.2 Assemble all documents for PR1
1.4.1.3 Prepare and practice presentation
1.4.1.5 Post all info online
1.4.2 Progress report 2 (PR2)
1.4.2.1 Fill out progress report template
1.4.2.2 Prepare est. vs. actual hours summary
1.4.2.3 Assemble all documents for PR2
1.4.2.4 Prepare and practice presentation
1.2.2.5 Post all info online
1.4.3 Other monitoring and controlling
1.5 Closing
1.5.1 Project notebook
1.5.1.1 Assemble all documents for notebook
1.5.1.2 Receive project completion form from sponsor
1.5.1.3 Prepare final report
1.5.1.4 Prepare and practice final presentation
1.5.1.5 Post all info online
1.5.1.6 Final presentation completed (milestone)